## Feature Backlog
FamilyPulse — Feature Backlog
Legend: yellow cells are for the team to fill in (Owner, Priority on new rows). Status/Priority already set for Rex's work this session; update as things move.
Feature | Category | Description | Status | Priority | Owner | Notes | Summary
Password show/hide toggle | Auth | Eye icon on password fields (login + signup) to reveal/hide input. | Done | High | Rex | Shipped this session. | Done | 20
Confirm email / confirm password | Auth | Signup gets a second email field and second password field, validated to match, with live re-check as you fix a typo. | Done | High | Rex | Shipped this session. | Done (existing) | 4
Light / dark mode | Personalization | Full theme system (System/Light/Dark) via a persisted setting, real Material 3 dark palette. | Done | High | Rex | Persists across restarts via shared_preferences. | Roadmap | 1
Settings screen | Personalization | Appearance, your name (editable), your family (name/created/code+copy), calendar default, sign out. | Done | High | Rex | Was assigned to Tatu earlier — reassign Tatu to another item below. | Total features | 25
Sign-out confirmation | Auth | "Are you sure?" dialog before signing out, instead of an instant, unconfirmable logout. | Done | Medium | Rex | Applied to all 3 sign-out entry points (Pulse, Family Choice, Settings).
Family name + creation date | Family | Shown in Settings, pulled from the existing Firestore family doc. | Done | Low | Rex | No new backend needed — field already existed.
Referral / family code | Family | Family code (the Firestore family ID) shown with a Copy button in Settings and the post-create dialog. | Done | Medium | Rex | Kid-friendly polish (QR code, shorter code) still open — see roadmap.
Personal display name edit | Personalization | Edit your own name from Settings; updates Firebase Auth profile. | Done | Medium | Rex
Multiple users per family | Family | Firestore members subcollection already supports any number of members. | Done (existing) | - | Igor | Confirm this is still true once Igor/Tatu's work merges in.
Unique user IDs | Family | Every user already has a Firebase Auth UID; used throughout for events/membership. | Done (existing) | - | - | Already working — no build needed.
Create a family | Family | Existing flow: name + your name, generates a shareable code. | Done (existing) | - | -
Join a family | Family | Existing flow: code + your name + role. | Done (existing) | - | -
Analytics page | Insights | Stats on family activity: total events, busiest day of the week, who's added the most, category breakdown, next-7-days load. | Done | High | Rex | Built as a client-side view over existing event data — no new backend needed, as planned.
Free time finder | Calendar | Overlays every member's events to highlight shared open windows; tap a slot to create an event there. | Done | High | Rex (screen) / Igor (backend) | EventService.findFreeSlots() was Igor's; the screen consuming it was built this session.
Fix dead /family and /free-time links | Navigation | Pulse's "Family" and "Free time" buttons used to throw GoException — both routes are now wired up, plus new Groups/Analytics/Profile routes. | Done | High | Rex | Also added the Groups, Analytics, and Profile routes as part of the same pass.
Create a group (sub-group in family) | Family | A named sub-group (e.g. "Kids", "Chores squad") holding a subset of family members. | Done | Medium | Rex | MVP: name + member picker, create/rename/delete. No group-specific calendar yet — that's still future scope if wanted.
Personal profile + nav redesign | Navigation | Left-side navigation drawer (Home, Calendar, Family, Groups, Free time, Analytics, Profile, Settings) plus a dedicated Profile screen. | Done | Medium | Rex | Profile edits now keep Firebase Auth's displayName and the Firestore member doc in sync — previously Settings only updated Auth, silently drifting from the Family roster.
Parent can rename other members | Family / Roles | A parent can edit another member's display name and label directly from the Family screen. | Done | Medium | Rex | Enforced server-side too: firestore.rules restricts a non-self update to exactly the name/label fields, and only when the caller's own role is 'parent'.
Expanded roles | Family / Roles | Role list expanded from parent/child to parent/child/guardian/other. | Done | Low | Rex | Only 'parent' unlocks parent-only actions — adding a role doesn't by itself grant new permissions.
Differentiate both parents | Family / Roles | Optional free-text label ("Mom", "Dad", "Grandma") shown alongside the role, settable by each member for themselves or by a parent for someone else. | Done | Low | Rex | Deliberately simple (free text, not a fixed enum) so it fits any family shape, not just a two-parent household.
Event categories | Calendar | Real categories (School / Hobby / Work / Other) with distinct icons and colors — previously every event silently saved as "other" with no way to change it. | Done | Medium | Rex | Unlocked the Analytics page's "by category" breakdown, which wasn't meaningful until this landed.
Color theme picker | Personalization | Six named color palettes (Blue Rose, Sunny Meadow, Coral Reef, Ocean Pop, Berry Patch, Aurora) selectable in Settings, each a real two-tone Material 3 scheme, persisted per user. | Done | Medium | Rex | Kid-friendly by design — selection uses a ring + checkmark, not color alone.
English / Finnish / Swedish localization | Personalization | Full app translation (206 strings) via flutter_localizations + intl, with a Language picker in Settings (System/English/Suomi/Svenska); dates and times are locale-aware via DateFormat. | Done | High | Rex | Also localized auth/family error messages, not just static UI labels.
Profile photo, age & gender | Personalization | Edit Profile now includes an avatar (camera or gallery, uploaded to Firebase Storage) plus optional age and gender fields, shown on the Profile screen. | Done | Medium | Rex | Storage rules restrict writes to your own file (5MB cap, images only); project upgraded to Blaze with a $1 budget alert so cost stays at $0.
Recurring events & reminders | Calendar | Repeating events (e.g. weekly practice) and reminder notifications ahead of an event. | Roadmap | Medium | TBD | Still open — meaningfully bigger scope (recurrence rules, notification scheduling) than the category work.

## Contribution Log
FamilyPulse — Team Contribution Log
Legend: yellow cells (Hours Logged) are estimates for each person to fill in / confirm themselves — do not guess on someone else's behalf.
Team Member | Focus Area | Key Contributions So Far | Hours Logged (self-reported) | Notes
Rex | Flutter build / Firestore / UX | Firestore wiring for calendar & events (create/edit/delete), validation and error/success UX across auth + event editor, Welcome screen and auth gating, sign-out relocation + confirmation, theme system + Settings screen, Firestore security-rules fix for first-time family joins, Analytics page, Free Time finder screen, Family Groups, expanded roles + parent-rename (with matching security rules), real event categories, nav drawer + Profile screen, CI build-failure email alerts, several bug fixes (dialog crash, family-code race, pre-commit hook). | 200 | Self-reported by Rex (as of Aug 26, 2026): ~200 hours total across research, core app build, Firebase/Storage setup, and CI/CD pipeline work. An estimate, not independently timestamped.
Jimmy Söderström | Report / documentation | Offered to start the report skeleton (intro/overview, architecture summary, contributions section). |  | Confirm current status directly with Jimmy.
Igor Smirnov | Backend / calendar logic | Built EventService.findFreeSlots(). Also spent recent weeks on a parallel FlutterFlow prototype — see report's Lessons Learned re: consolidating on one build. |  | As of Aug 26, 2026: focused on the separate FlutterFlow build rather than this codebase — confirm current status and plans directly with Igor.
Tatu Ekroth | TBD — reassign | Settings screen was assigned here but got built this session (see Feature Backlog) — needs a new assignment. Also spent recent weeks on the parallel FlutterFlow prototype. |  | As of Aug 26, 2026: focused on the separate FlutterFlow build rather than this codebase — confirm current status and plans directly with Tatu.
|  | Total hours logged | 200